## Portal
# | Communication activity | Description | Timeline | Student or Staff comms plan (filter on student & both or staff & both) | Audience Grouping | Key Messages | Strategic Plan/KPI link | Values | Current Portal | New Portal | Email (incl signatures) | VC Email | Greenwich Online | Newsletter | F2F (meetings, workshops) | FAQs ,Presentation, Report | Roadshow | Manager cascade | Blog | Video | Digital Signage | Social Media | Survey | Share update with Faculty staff | Draft comms needed by [date] | Date live | Action by | Mark as complete | Project tab
1 | Changes to Portal Groups | 'groups' funcitonality is changing | June | Staff | All Staff | it's changing, get in touch if you use regularly |  |  |  |  | X | [14 empty] | 2016-06-30 | ILS HelpDesk | Y
2 | Changes to Portal Groups | 'groups' functionality no longer available in new portal | Mid-August | Staff | All staff | work with individuals to address concerns; from November current groups no longer available; how to request content not retrieved by end-October |  |  |  |  | X |  |  |  | X | [10 empty] | 2016-08-19 | Jeremiah, Robin, Dean | Y | Portal
3 | Changes to Portal Groups | 'groups' functionality no longer available in new portal; information for group owners | Early-Sept | Staff | Group owners | Reminder functionality will be removed and content owners should download content by end-October. Offer to work with group owners to identify best tools for ongoing requirements | [19 empty] | 2016-09-08 | ILS HelpDesk | Y
4 | FOO Cascade | Update for PVCs, FOOs, DSEs and DLTs to inform work is completing to relaunch the Portal, | Mid-September | Staff | Senior Managers | the portal is changing; relaunch early November; informed by workshops; will deliver [benefits]; comms will start early October |  |  |  |  | X | [13 empty] | - | 2016-09-14 | Clifton | Y
5 | Awareness for Content Owners | Provide information and assurance about their content | End-September | Staff | Content Owners | Summary of Web Editors update; include visuals, reassurance on where content is moving too, what action they'll need to take & tools available to help. Advise their colleagues help documentation needs updating. |  |  |  |  | X |  |  |  |  | X | [9 empty] | 2016-09-23 | Rayna, Jeremiah, Robin, Dean | Y | Portal
6 | Update for Web Editors | Robin to show the Web Editors the new portal, provide an opportunity for them to ask questions | Mid-September | Staff | Web Editors | It's developed and looks like this; the benefits are…; your role is [monitor, stats, future changes]; new portal will be a key part of how we communicate with staff; have we missed anything; share comms plan; answer questions; let content owners know the change is coming. CARE: audience group is a busy one, their role now to advise others, give feedback and raise awareness of the new portal |  |  |  | Demo |  |  |  |  | X | X | [9 empty] | 2016-09-27 | Jeremiah, Robin, Clifton & Stephanie | Y | Portal
7 | Awareness for Service owners | Provide information and assurance about their content | 2016-09-01 | Staff | Service Owners | Summary of Web Editors update; include visuals, reassurance on where content is moving too, what action they'll need to take & tools available to help. Advise their colleagues help documentation needs updating. |  |  |  |  | X | [14 empty] | 2016-09-30 | Rayna, Robin | Y
9 | Content owners - UAT action needed | Ask to check links on the UAT portal | 2016-10-01 | Staff | Content owners | The portal is changing (recap); what you need to do and information on UAT |  |  |  |  | X | [14 empty] | 2016-10-03 | Rayna, Robin | Y
11 | Update for ILS strategy board | Paul to provide an update so they know what the new portal looks like, when it's coming and what it means for their faculties/directorates; Action: to cascade to management teams. | Early-October | Staff | ILS Strategy Board | What it looks like; key changes (= key messages) go-live plan including planned communications; longer term governance & management; how staff engage with the home tab |  |  |  | Demo |  |  |  |  | X | X | [8 empty] | 2016-09-28 | 2016-10-05 | Paul to present with support from Robin/Dean; Information from, Clifton, Jeremiah & Stephanie | Y | Portal
12 | Update for CCG | Clifton to update CCG as per ILS strategy board update in early October (CCG meeting is on 11 October) | Mid-October | Staff | CCG | What it looks like; key changes (= key messages) go-live plan including planned communications; what happens next | [8 empty] | X | X | [9 empty] | 2016-10-11 | Clifton & Stephanie | Y | Portal
13 | content on the current portal | Advertising the portal is changing, why and benefits (exclude date) | Mid-October | Staff | Staff portal users | Portal Announcement: The portal is changing and why, its benefits (use key messages & supporting messages document) |  |  | X | [16 empty] | 2016-10-18 | Dean, Richard, Rayna, Stephanie | Y | Portal
14 | content on the current portal | Advertising the portal changes, where to find more info | Mid-October | Students | Student portal users | Portal Announcement: The portal is changing and why, its benefits (use key messages & supporting messages document) |  |  | x | [14 empty] | X |  | 2016-10-18 | Dean, Richard, Rayna, Stephanie | Y
15 | Briefing for Help Desk teams | Awareness ahead of go-live and in preparation for go-live calls | Mid-October | Both | Help Desk teams | Equip teams to provide first line support; know why things have changed and where they are and how to escalate questions | [8 empty] | X | X | [9 empty] | 2016-10-18 | Rayna | Y
16 | Briefing for Enquiry Unit | Awareness ahead of go-live and in preparation for go-live front-line | Mid-October | Both | Enquiry Unit staff | Equip teams to provide first line support; know why things have changed and where they are and how to escalate questions | [8 empty] | X | X | [9 empty] | 2016-10-18 | Rayna | Y
17 | Briefing for Library staff | Awareness ahead of go-live and in preparation for go-live front-line | Mid-October | Both | Library staff | Equip teams to provide first line support; know why things have changed and where they are and how to escalate questions | [8 empty] | x | X | [9 empty] | 2016-10-18 | Rayna | Y
18 | FOO Cascade | email to FOOs following steering group meeting | Mid-October | Staff | Senior Managers | Focus on cutover weekend/no submissions, no availability for portal. Ask them to cascade this message; share new screeshots |  |  |  |  | x | [14 empty] | 2016-10-19 | Clifton | Y | Portal
19 | Referenced in Roadshow invite | Awareness: new portal on the agenda, demo's available etc | Mid-October | Staff | All Staff | It's changing, it's part of the roadshow, come along and see ore |  |  |  |  | x | [13 empty] | n/a | 2016-10-19 | Laleh/Stephanie | Y | Portal
22 | The portal is changing | All staff email | Mid-October | Staff | All staff | Summary of It's changing message; login screen info; unavailable 5-6 Nov & key new features |  |  |  |  | X |  |  |  |  | X | [8 empty] | 2016-10-20 | 2016-10-24 | Stephanie, Clifton, Rayna | Y | Portal
23 | Reminder: Portal is changing on 7 November - login page | Make use of digital signage and existing portal (replacing Portal is changing imagery) | End-October | Students | Students | Highlight change is taking place on 7/11 on login page |  |  | x | [16 empty] | 2016-10-24 | Clifton | Y
24 | Reminder: Portal is changing on 7 November - login page | Make use of existing portal; replace Portal is changing imagery | End-October | Staff | All staff | Highlight change is taking place on 7/11 on login page |  |  | x | [16 empty] | 2016-10-24 | Clifton | Y
26 | The portal is changing | Preparing students for go-live | Mid-October | Students | Students | similar to staff information but with a student focus; start a trickle on social media |  |  |  |  | X | [9 empty] | X | X |  | X | 2016-10-20 | 2016-10-24 | Richard/ Alex | y | Portal
27 | Feature in Greenwich Online | Recap of when, why it's changing and what it means for staff | Mid-October | Staff | All staff | Authored article - It's changing, benefits, what you need to do, longer term vision ++ include visuals | [6 empty] | X | [12 empty] | 2016-10-27 | Clifton, Stephanie | Y | Portal
28 | Update for CSG (Comms Strategy Group) | email update with screenshots (next meeting is 31 October) | Mid-October | Staff | CSG | What it looks like; key changes (= key messages) go-live plan including planned communications; longer term governance & management. No course submissions. FOOs cascade to staff | [8 empty] | X | X |  | X | [7 empty] | 2016-11-03 | Clifton, Rayna, Stephanie | Y
31 | The portal is here | Welcome to the new portal | Go-Live | Staff | All staff | Welcome news item, reminder of what's changed, links to annotated pdf's, where to get help, FAQ how to, video overviews |  |  |  | X | [5 empty] | X |  |  |  | X |  |  |  |  | 2016-10-31 | 2016-11-05 | Stephanie | Y | Portal
32 | The portal is here | Welcome to the new portal | Go-Live | Students | Students | Welcome news item, reminder of what's changed, links to annotated pdf's, where to get help, video overview / how to |  |  |  | X | [5 empty] | X |  |  |  | X |  |  |  | X | 2016-10-31 | 2016-11-05 | Richard/ Alex | Y
33 | Agree contingency comms in advance | have pre-written content (with blanks); agreed recipient list | Early-November | - | [6 empty] | X | [13 empty] | 2016-11-01 | 2016-11-05 | Rayna | Y
34 | Agree success comms in advance | have pre-written content; agreed recipient list | Early-November | [7 empty] | X | [13 empty] | 2016-11-01 | 2016-11-05 | Rayna | Y
37 | The new portal at the EE roadshows | Opportunity to find out more about the portal now that it's live | Early-November | Staff | All staff | Share benefits and changes, initial feedback, longer-term vision. Breakout demos in smaller groups (iPads) |  |  |  |  | Demo | [5 empty] | X | [8 empty] | 2016-11-09 | Clifton, Laleh, Stephanie | Y | Portal
38 | Introductory information/invites for EE roadshows | Provide content to entice people along to the Roadshows and hear more about the Portal, it's uses etc | Mid-October | Staff | All staff (via HR) | The Portal has changed; demo of key features; smaller demos is informal networking slot [Invites will be sent week of 10/10] | [10 empty] | X | [8 empty] | 2016-11-09 | Stephanie | Y | Portal
39 | [28 empty] | Portal
40 | [28 empty] | Portal
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55

## Comms "collateral" (hidden)
What | Audience | Needed for | Re-usable? | Where used | Link or location | Complete | Created by | Status
Key messages & supporting messages | university-wide | 2016-09-20 | Yes!! | [use throughout our comms] | https://uogcloud-my.sharepoint.com/personal/bj44_gre_ac_uk/_layouts/15/guestaccess.aspx?guestaccesstoken=pmLYxbgTYpyc8xT0XMtgNyA6sxkoehaf8IBsgnFHqws%3d&docid=2_1130c0ccea19d445896cdc29223b0f77b&rev=1 | Yes | Stephanie | Available
Presentation | Web Editors | 2016-09-25 | Yes - with edits | 26/9 Web Editors meeting | https://uogcloud-my.sharepoint.com/personal/bj44_gre_ac_uk/_layouts/15/guestaccess.aspx?guestaccesstoken=w4a4wlMpWu4lr00pEaWRbAmzL6Sg1eJPCo78YaNcGyA%3d&docid=2_193cf30966afd427eb1ef1ada9f0da0fc&rev=1 | Yes | Stephanie, Jeremiah, Rayna, Robin & Clifton | Presented at September Web Editors group; used at Oct CCG for verbal update
Information paper | ILS strategy board | 2016-09-28 | Yes - with edits | October meeting | https://uogcloud-my.sharepoint.com/personal/bj44_gre_ac_uk/_layouts/15/guestaccess.aspx?guestaccesstoken=4W4KA3%2bhorPK89bihjJZqIHBHLle8Bom7GORoYYCa7U%3d&docid=2_1196226678e9d44b8b217d9063d869d9f&rev=1 | Yes | Stephanie, Robin, Clifton & Paul B | With Paul B
Portal is coming message | university-wide | 2016-10-12 | Yes | Existing portal from 12/10 | https://uogcloud-my.sharepoint.com/personal/bj44_gre_ac_uk/_layouts/15/guestaccess.aspx?guestaccesstoken=5DY5pOINSo47qzeSBF8Y47nR35gEmobmN%2b0VZQWNc3g%3d&docid=2_139313c19ec2c4396b0b6aad2526815bc&rev=1 | Yes | Stephanie | with Rayna to arrange publication
Portal one pager | All Staff | 2016-10-18 | Yes |  | [before 18/10 use key messages & supporting messages document above] |  | Stephanie
Portal is coming, it looks like this | university-wide | 2016-10-19 |  | Existing portal from 19/10 | [may no longer need: as portal is coming message now on 18/10] | - | Stephanie
Portal is coming All Staff email | All Staff | 2016-10-21 | Yes |  | https://uogcloud-my.sharepoint.com/personal/bj44_gre_ac_uk/_layouts/15/guestaccess.aspx?guestaccesstoken=FBWz%2bEj12apD02XX9ybc%2b8GI6wqta1Y5LRBtotQihE4%3d&docid=2_1f82326bf77e942e3babb59e7ec1fa252&rev=1 | Yes | Stephanie
Greenwich online article | All Staff | 2016-10-24 | [can link to] | Greenwich online | https://uogcloud-my.sharepoint.com/personal/sr5774h_gre_ac_uk/_layouts/15/guestaccess.aspx?guestaccesstoken=RooVbf5TuyQnX5pcJHJeAdjcFh8AecZ4aY3e7zLwYZI%3d&docid=2_1ef89cd3ca8fd44e593c0dfc2ff1d6f66&rev=1 | Yes | Stephanie, Clifton
Welcome to the new portal | All Staff | 2016-11-01 | Y | News for staff portlet |  | DRAFT THIS | Stephanie
Annotated pdf (highlighting changes) for staff | All Staff | [5 empty] | Rayna
Video - changes for staff | All Staff | [5 empty] | Rayna
Annotated pdf (highlighting changes) for students | Students | [5 empty] | Rayna
Video - changes for students | Students | [5 empty] | Rayna
Digital signage | Students | [5 empty] | Richard
Where to find things on the new Portal document | university-wide |  | Yes | New portal [single document for content owners to link to] |  |  | Richard
FAQs | university-wide |  | Yes |  |  |  | Rayna
FAQs | university-wide | [5 empty] | Rayna
Portal feedback email (temporary mailbox for feedback) | university-wide |  | - |  |  |  | Rayna
Contingency comms | [6 empty] | Rayna
Success comms | [6 empty] | Rayna
Portal documents are stored here: |  |  |  |  | https://uogcloud-my.sharepoint.com/personal/bj44_gre_ac_uk/_layouts/15/onedrive.aspx?id=%2fpersonal%2fbj44_gre_ac_uk%2fDocuments%2fPortal+Project%2fMoved+to+one+drive&FolderCTID=0x012000C05A84E9179B554FB48C9339B80223A0